## Topsfield Draft
Topsfield Downtown Revitalization Plan Implementation Matrix
Timeline: Immediate: Within 1 year; Near-term: 1-2 years; Mid-term: 2-3 years; Long-term: 4+ years; Ongoing
| Goal/Strategy/Action | Parties Responsible | Timeline | Potential Resources (Technical assistance and/or funding opportunities)
Economic Development
GOAL 1: ATTRACT NEW BUSINESSES TO THE DISTRICT TO RESPOND TO THE NEEDS OF TOPSFIELD RESIDENTS
Strategy 1: Review and Update Zoning
| 1A: Explore re-zoning the town common and abutting lots to create a new Common District. Such a zoning district should preserve the character of the common, but expand permitted uses to include selected businesses such as guest houses, restaurants, and business offices. | TA, BOS, Planning Board | Immediate
| 1B: Explore modifying existing zoning regulations to: --Adjust required setbacks for downtown development since most buildings are currently non-compliant, and any building changes/new construction requires ZBA review. --Permit 3-story buildings (commercial and residential) in the Business Village District (BVD) to spur investment and increase the financial viability of such projects. --Increase parking flexibility through parking minimums for businesses and resident on Main Street in the Downtown. Increase parking flexibility through the following longer-range actions: a. Allow shared parking to meet requirements–Esp. in mixed-use developments b. Allow change-of-use below a certain threshold c. Require bicycle parking d. Design considerations e. Limit curb cuts f. Minimum/maximum widths for driveways | TA, BOS, Planning Board | Near-term Mid-term
| 1C: Review and update licensing and permitting procedures for businesses, such as the one-day liquor license. | TA, BOS, Alcohol Advisory Board | Immediate
Strategy 2: Improve District Infrastructure
| 2A. Evaluate the need to expand sewer capacity in the district; investigate the capacity of several key parcels to determine development options; based on findings, investigate scope, options, feasibility, and costs. | TA, BOS, Planning Board | Mid-term
| Strategy 3: Connect current property owners and developers with prospective business owners, developers, and industry representatives of key needed and desired businesses to discuss options for adding housing, bringing in new businesses, and expanding current businesses that are reflective of the community vision | TA, BOS, Planning Board | Near-Mid term
| Strategy 4: Evaluate opportunities to help finance future development of new businesses utilizing District Increment Financing in the re-zoned area around the commons and abutting lots. | TA, BOS, FinCom, Accountant, Assessor | Near-term
GOAL 2: INCREASE THE CUSTOMER BASE IN THE DISTRICT TO SUPPORT DOWNTOWN BUSINESSES BY ADDING HOUSING, AND MARKET THE VILLAGE TO RESIDENTS AND VISITORS.
Strategy 1: Add housing in the BVD
| 1A: Meet with property owners to explore interest in adding housing to their current properties, building on current structures or building new structures), and gather input on the height and density needed to make housing and mixed-use development financially viable. | TA, Planning Board, BOS, Building Inspector, Health Agent, Property Owners | Near-term
| 1B: Explore new zoning regulations to encourage housing and mixed-use development in the downtown. To encourage this development, new regulations will need to be more flexible. The following changes should be considered: --Reduced minimum lot area, lot frontage, lot depth, parking requirements, and minimum yard requirements to make it possible to develop on smaller parcels resulting in housing that is of a smaller scale and more naturally affordable. --Increased height, potentially up to three stories, to allow for more density that makes it possible to build the number of housing units needed to make a project financially viable and attractive to developers. | TA, Planning Board, BOS, Building Inspector, Health Agent | Mid-term
| 1C: Include development standards and design guidelines in the zoning to ensure the architecture and style of new housing developments are consistent with the rural character of the Town. | TA, Planning Board, BOS, Building Inspector, Health Agent | Mid-term
| 1D: Apply 40B Guidelines (in development) to the extent possible in order to meet state requirements with acceptable, affordable housing options. | TA, Planning Board, BOS, Building Inspector, Health Agent | Mid-term
| 1E: Evaluate the feasibility of revising current zoning regulation to allow for occupancy of accessory dwelling units by non-family members to increase housing options within the BVD. | TA, Planning Board, BOS, Building Inspector, Health Agent | Near-term
| Strategy 2: Pursue a Housing Production Plan for Topsfield (some funding may be available from MAPC through the technical assistance program). | Town Administrator, Planning Board, BOS, Building Inspector, Health Agent, Fincom, Accountant | Mid-term
Strategy 3: Expand marketing efforts
| 3A: Work with business owners to create joint marketing materials and initiatives and strategy for advertising. | TA, Business Owners | Near-term
| 3B: Coordinate with Topsfield Fairgrounds to market downtown activities to Fairground event attendees. This could include Direction and Promotional signage and downtown parking arrangement for Fair attendees to attract them to businesses in the Downtown | TA, Jamie O'Brien, Highway, Police Dept | Immediate
Strategy 4: Improve parking and traffic management through implementation of the Downtown Parking Study.
| 4A: Add signage and wayfinding tools including: --sign on Main Street directing to Public Lot on School Street–Add sign at Public Lot --sign near MBTA lot directing to downtown Topsfield --signage for MBTA lot near the rail trail | TA, BOS, Planning Board, Highway, Police Dept | Near-term
| 4B: Create a parking map for the Town website. | Town Administrator, Sue Winslow | Immediate
| 4C: Create 2-hour time limits for parking spaces in front of Post Office and between Central and School Street, coupled with long-term parking option. Enforce time limits - considerations: 1. First Ticket Free 2. Provide a parking map with tickets so drivers know where they can park. Monitor and adjust. | TA, Highway, Police Dept, BOS, Planning Board | Immediate
| 4D: Pursue shared parking agreements with Topsfield Shopping Center, St. Rose of Lima Catholic Church, and local shop owners. Agreements can be for: i. Select groups, i.e., residents or employees ii. General public iii. Limited hours Provide services in exchange for open parking (i.e., plowing, signage, striping, signage, plantings, etc.) | TA, Highway, Police Dept, BOS, Planning Board, Accountant, FinCom, Legal | Near-term
| 4E: Make a pedestrian-friendly walkway to the public lot on School Street | TA, Highway, BOS, Planning Board | Immediate
| 4F: Add lighting to the public lot on School Street | TA, Highway, BOS, Planning Board | Immediate
| 4G: Add a crosswalk to Main Street, north of Central Street | TA, Highway, BOS, Planning Board | Near-term
| 4H: Add drop-off Post Office box to alleviate congestion on the Post Office | TA, Highway, BOS, Planning Board, Post Office, Mr. Flomp | Near-term
| Strategy 5. Explore traffic calming measures that are conducive to community building (such as road and sidewalk design, pavement murals and stencils). | TA, Highway, BOS, Planning Board, Police Dept. | Mid-term
| Strategy 6. Determine traffic management needs and potential solutions (signage, lane design, and markings, signalization, etc.) | TA, Highway, BOS, Planning Board, Police Dept. | Mid-term
GOAL 3: ENHANCE THE LOOK, FEEL AND SAFETY OF THE DISTRIC TO MAINTAIN A VIBRANT AND WALKABLE DOWNTOWN, AND CREATE A SENSE OF PLACE WHERE ALL CAN GATHER.
| Strategy 1: Develop a public space improvement plan with design guidelines and establish key locations for improvements to ensure coordination. Plan to include: --Aesthetic improvements to sidewalks at key locations, including amenities such as benches, tables, trash receptacles, attractive warm lighting, kiosks, etc. --Evaluation of adding additional sidewalks in key locations determined to have high foot and vehicular traffic --Possible commission of local artists/residents/students to paint murals on key sites in the district --Exploring the feasibility of installing Bigbelly solar-powered trash compactor bins that reduce hours spent on collection and maintain a vibrant downtown district --Adding bike racks in key locations to encourage biking and safe storage of bikes away from business entrances | TA, BOS, Highway, Police Dept., Schools, Business Owners, Accountant, Fincom, Parks & Cemetary, Recycling Task Force, TCP | Near-term
| Strategy 2: Conduct a study to investigate the feasibility of grounding overhead utilities to improve the appearance and function of downtown spaces. | TA, BOS, Highway, Accountant, Fincom | Long-term
| Strategy 3: Implement improvements to the facades and signage of businesses in prominent locations. | TA, BOS, Business/Building Owners, TCP | Near-mid term
| Strategy 4: Install street banners to enhance the look of downtown to promote events | TA, Highway, TCP | Near-term
Strategy 5: Improve district lighting
| 5A. Improve the lighting near Town Hall, around the Common and in the Municipal Parking Lot. | TA, BOS, Highway, Fincom, Accountant | Mid-term
| 5B. Consider lower-wattage warm LED lighting in pedestrian areas. | TA, BOS, Highway, Fincom, Accountant | Near-term
| 5C. Consider installing decorative or historical solar-powered street lamps along downtown Main Street. | TA, BOS, Highway, Fincom, Accountant | Mid-term
| 5D. Use string lighting over the street or other decorative lighting to enhance the sense of place in downtown. | TA, BOS, Highway, Fincom, Accountant, Business Owners | Near-term
| Strategy 6: Install directional and promotional signage to direct visitors to the Downtown including signs at: --Rte. 1 at South Main St. and Central St. --Rte. 97 --in the downtown with directions to key locations (parking, key amenities) --at the intersection in front of Town Hall/Library --other locations | TA, BOS, Highway, Fincom, Accountant,Planning Board, Building Inspector | Near-term
| Strategy 7: Install a prominent town kiosk that can be a central information space for the community including historical information about Topsfield | TA, BOS, Highway, Fincom, Accountant,Planning Board, Building Inspector | Mid-term
Strategy 8: Add plantings to the district with continued watering and maintenance, while ensuring that choice of plantings and watering procedures support and abide by water conservation guidelines
| 8A. Add potted aerial plants and planters with flowers in key locations throughout the downtown. | TA, Planning Board, Business Owners, Parks & Cemetery, TCP | Immediate
| 8B. Add groundcover plantings in front of or between key businesses in the district. | TA, Planning Board, Business Owners, Parks & Cemetery, TCP | Immediate
| 8C. Incentivize improved landscaping at private properties through small grants & low-key competitions/exhibitions for attractive displays. | TA, Planning Board, Business Owners, Parks & Cemetery, TCP | Mid-term
Strategy 9: Install community amenities to create a sense of place and attract residents and visitors to the downtown
| 9A. Install benches at key locations in the business district to increase gathering spaces for community members and visitors | TA, BOS, Planning Board, Business Owners, Parks & Cemetery, TCP | Immediate
| 9B. Evaluate the feasibility of creating a dog park in or adjacent to the business district | TA, Planning Board, Parks & Cemetary | Immediate
| 9C. Explore areas where pocket parks (approx. 100-600 sf) could be added to bring more activity to downtown. | TA, Planning Board, Parks & Cemetary | Immediate
| Strategy 10: Explore the feasibility of expanding recreational areas/facilities including: --Outdoor Hockey Rink (ie, a portion of the Proctor School ballfield/playground during the winter) --New nets on Proctor Field --Mountain Biking Trail --Community Pickle Ball Court/BBall --Rec Center | TA, BOS, Planning Board, Parks & Cemetary, Proctor School | Near-term Immediate Near-term Mid-term Mid-term
| Strategy 11: Collaborate with the Congregational Church to improve the brick entrance to Emerson Center ( intersection of Rt 97 and Main St.) | TA, Congregational Church, TCP | Immediate
| Strategy 12: Develop a plan for enhancing landscaping to allow sight of key historic buildings along Main St. (Town Hall, Proctor School, Library) to create a more attractive and pedestrian-scale feel. | TA, BOS, Schools, Planning Board, Highway, Parks & Cemetary | Immediate
| Strategy 13: Fix the town hall clock to highlight its historic value and accuracy, and add night lighting | TA, Historical Society, Town Hall Building Committee | Immediate
GOAL 4: INCREASE COMMUNITY-BUILDING EVENTS IN THE DISTRICT TO AMINTAIN A MORE ENERGETIC DOWNTOWN.
| Strategy 1: Explore the idea of town-sponsored food truck events. Possible locations include the Essex Coop (which already hosts food trucks), downtown, along the Common, in Park St parking lot adjacent to the Rail trail, etc. | TA, Essex Coop, Parks & Cemetary, Health Agent, Police Dept | Near-term
| Strategy 2: Explore the creation of recreational events Downtown or on the Common (such as Giant backyard games, mini-golf, concerts, Pop Up events, festivals, road races, etc.) | TA, Parks & Cemetary, Police Dept | Near-term
GOAL 5: EXPAND TOWN CAPABILITIES AND RESOURCES TO ACHIEVE THESE GOALS.
| Strategy 1. Hire a part-time Town Planner with the goal of: i. Coordinating town-wide planning efforts. This includes: 1. Leading the implementation of the Downtown Revitalization Plan, in partnership with a Downtown Oversight Group. 2. Leading efforts to address housing needs, such as a Housing Production Plan, and a review of affordable housing options beyond 40B. The planner should also incentivize housing options through a clear and easy permitting process that ensures the Town’s development goals are achieved. 3. Serve as a town Development Officer charged with attracting and engaging potential new businesses and activities, and with facilitating smooth, efficient processes for applicants working with various Town Departments. ii. Developing new funding sources through grant applications and other efforts. 1. Consider creating a part-time grant-writing position to assist in the timely application for available assistance with the state and others. | Town Administrator, BOS, FinCom, Planning Board | Immediate
| Strategy 2: Establish a Downtown Revitalization oversight group made up of Topsfield residents, business owners, and Town officials to ensure momentum and communication on progress continues. | Town Administrator, BOS | Near-term
| Strategy 3: Solicit a volunteer Downtown maintenance group to provide continued care to the downtown (landscaping, other improvements) | Town Administrator, BOS, Garden Clubs | Immediate
| Strategy 4: Work closely with the Topsfield Community Partnership (TCP) to coordinate town and TCP activities to help revitalize the downtown. | Town Administrator, BOS, TCP | Ongoing
| Strategy 5. Facilitate the creation of a Topsfield business group to assist with joint promotion and downtown revitalization efforts. | Town Administrator, BOS, Business Community | Near-term

## Cohasset MP Example
Cohasset Master Plan Implementation Matrix
Timeline: Near-term: 1-3 years; Mid-term: 4-6 years; Long-term: 7+ years; Ongoing
| Goal/Strategy/Action | Parties Responsible | Timeline | Potential Resources (Technical assistance and/or funding opportunities)
Transportation & Circulation
Goal 1: Improve pedestrian connectivity throughout the Town
| Strategy 1.1: Enroll in MassDOT Complete Streets Program | TP | 1-3 | MassDOT Complete Streets program
| Strategy 1.2. Improve safety, mobility, and access on Route 3A for all types of transportation | DPW | Ongoing | MassDOT, FHWA Road Safety Audit guidelines
| Strategy 1.3: Construct pedestrian facilities in other high traffic locations throughout Town | DPW | 4-6 | MassDOT Complete Streets program
| Strategy 1.4: Consider other initiatives to improve pedestrian safety and convenience | TP | 4-6 | MassDOT Complete Streets program
Goal 2: Improve bicycle access and safety
| Strategy 2.1: Implement on-road bicycle infrastructure | DPW | 7+
| Strategy 2.2 Improve and connect off-road multi-modal facilities | OSRC | 7+ | MAPC Landline, MAPC Trail Implementation Toolkit
Goal 3: Improve how roadways in Town operate
| Strategy 3.1 Improve mechanisms for addressing private ways | BOS, TP, PB | 1-3
| Strategy 3.2 Address local parking challenges and opportunities | TP, DPW | 4-6
| Strategy 3.3 Improve roadway safety and operations | DPW | Ongoing | MassDOT, FHWA Road Safety Audit guidelines
Public Facilities & Services
Goal 1: Ensure Cohasset’s public infrastructure and facilities meet community and departmental needs
| Strategy 1.1: Maintain and refine the Town’s capital planning and implementation processes | Cap, TM, BOS | Ongoing
| Strategy 1.2: Plan for the renovation or replacement of facilities whose size, condition, and/or location inhibit the efficient operation of the Town staff and citizens who rely on them | Cap, TP, TM, BOS | Ongoing | CPA, MPPF, MA School Building Authority, MA Board of Library Commissioners
| Strategy 1.3: Continue to identify and proactively address maintenance concerns which do not yet rise to the level requiring capital improvement funding | All departments | Ongoing
| Strategy 1.4: Consider department’s capital assets portfolio holistically and evaluate opportunities to share or transfer resources between departments | Cap, TM, BOS | Ongoing
| Strategy 1.5: Upgrade the technology infrastructure of public buildings to improve their operations | All departments | Ongoing
| Strategy 1.6: In addition to attaining or maintaining compliance with the Americans with Disabilities Act (ADA), consider designing public facilities in line with the principles of universal design (UD), also called inclusive design, which seeks to create spaces that can be used by all people, regardless of their age, size, disability or ability | TM, TP | Ongoing
Goal 2: Secure and supply adequate resources to provide high quality facilities, services, and programs that serve the needs of Cohasset’s residents
| Strategy 2.1: Continue to foster relationships between the Town government and community partner organizations and share resources to aid each in the fulfillment of their missions | TM, BOS | Ongoing
| Strategy 2.2: Encourage and support the continued pursuit of grant funding and other alternative financing strategies | TM, BOS, TP | Ongoing
| Strategy 2.3: When evaluating capital purchase requests for specialized equipment, gains to staff productivity and work efficiency should be considered in addition to the base cost | Cap, TM | Ongoing
| Strategy 2.4: Continue to support the “One Community” initiative to foster resource sharing with all departments in Town to economically use tax revenue | TM, BOS | Ongoing
Goal 3: Enhance communication and improve transparency of town processes
| Strategy 3.1: Continue to disseminate information on town processes through all channels of communication | TM | Ongoing
| Strategy 3.2: Increase coordination between Town committees and boards | TM | Ongoing
| Strategy 3.3: Utilize established and emerging technologies to improve inter-department and intra-department communication | TM | Ongoing
Goal 4: Explore collaborative solutions to address regional issues facing the Town of Cohasset and neighboring communities
| Strategy 4.1: Work with surrounding communities to increase Cohasset’s resilience against the effects of climate change | TP | 1-3
| Strategy 4.2: Identify opportunities to coordinate with neighboring towns in addressing the environmental and other impacts of development in adjacent areas | TP | Ongoing
| Strategy 4.3: Continue, and consider expanding, participation in collective purchasing programs for capital equipment to benefit from economies of scale and save staff time | Cap, TM | Ongoing
Housing
Goal 1: Diversify Cohasset’s housing stock and promote increased options for households of varying sizes, incomes, tenures, and ages
| Strategy 1.1: Consider amending the Zoning Bylaw to allow context-appropriate increases in density in key areas of town, such as along Route 3A, near the train station, in the harbor area, or near the village center | TP, AHSC, PB | 1-3 | EEA Planning grants, MassHousing grants
| Strategy 1.2: Identify areas to use zoning or other incentives to encourage “missing middle” typologies – buildings that fall between single-family houses and small-scale multifamily buildings | TP, AHSC, PB | 1-3 | EEA Planning grants, MassHousing grants
| Strategy 1.3: Review the zoning regulations to more fully encourage the construction of accessory dwelling units (ADUs) | TP, AHSC, PB | 1-3 | EEA Planning grants, MassHousing grants
| Strategy 1.4: Develop a local program to support first-time moderate-income homeowners seeking to purchase a home in Cohasset. | AHSC | 1-3 | Mass Housing Partnership
| Strategy 1.5: Develop a plan to outreach and engage with residents to promote a greater understanding of housing need and goals | AHSC | Ongoing
Goal 2: Increase the supply of deed-restricted affordable housing qualified for the state Subsidized Housing Inventory
| Strategy 2.1: Utilize CPA funds to support new affordable housing projects | CPC | Ongoing | CPA
| Strategy 2.2: Fund and empanel the Affordable Housing Trust Fund | BOS | 1-3 | CPA
| Strategy 2.3: Continue to seek partnerships with nonprofit developers and Community Development Corporations | TP | Ongoing
| Strategy 2.4: Provide municipal support to the prospective affordable housing developments | TP | Ongoing
| Strategy 2.5: Develop policies and programs that will aid Cohasset’s neediest residents | TP, AHSC | Ongoing
| Strategy 2.6: Complete a Housing Production Plan, currently underway, by summer 2019 | AHSC, TP | 1-3 | MAPC
| Strategy 2.7: Maintain safe harbor under Chapter 40B | AHSC, TP | Ongoing
Goal 3: Support seniors as they age and provide housing options that will enable them to live and thrive in Cohasset
| Strategy 3.1: Explore tools to help residents age in place | AHSC, EA | 1-3 | AARP
| Strategy 3.2: Promote age-friendly development that is sized for smaller households | AHSC, EA | Ongoing | AARP
| Strategy 3.3: Adopt visitability or universal design guidelines that encourage architectural approaches to new homes and home improvement projects that would increase accessibility for older adults and people with disabilities | AHSC, EA | 4-6
Energy & Sustainability
Goal 1: Reduce municipal energy use
| Strategy 1.1: Continue tracking and analyzing energy data in Mass Energy Insight (MEI) | AEC | Ongoing
| Strategy 1.2: Continue participation in the Green Communities program | AEC | Ongoing | Green Communities
| Strategy 1.3: Undertake an education/training campaign for municipal building staff and users | AEC, TM | Ongoing
| Strategy 1.4: Implement a strategy to track energy cost savings | AEC, TM | 1-3
| Strategy 1.5: Start research into Net Zero options and goals to inform an eventual municipal net zero plan | AEC | 1-3 | MA Department of Energy Resources (DOER) Pathways to Zero Net Energy Program
Goal 2: Reduce residential and commercial energy use
| Strategy 2.1: Promote MassSave for residential EE audits and incentives (targeted residential outreach where appropriate) | AEC | Ongoing | MassSave
| Strategy 2.2: Promote Property Assessed Clean Energy (PACE) financing mechanism for commercial energy efficiency and renewable energy work | AEC | Ongoing
| Strategy 2.3: Continue enforcement of the Stretch Energy Code for new buildings | B&I | Ongoing | Green Communities
Goal 3: Prepare for climate change and increase Town resiliency
| Strategy 3.1: Continue participation in the State’s Municipal Vulnerability Preparedness Program | TP | Ongoing | MVP Action grants
| Strategy 3.2: Use the results of the Harbor Plan to inform resiliency and climate adaptation planning and identify additional actionable priorities | TP, Har | Ongoing | MVP Action grants
| Strategy 3.3: Incorporate relevant knowledge of sea level rise and expected rainfall into all planning and permitting processes within the Town | TP, PB | Ongoing
| Strategy 3.4: Engage and educate the community around energy and climate issues | AEC | Ongoing
Goal 4: Promote the use of additional renewable energy to reduce emissions and costs
| Strategy 4.1: Participate in the Solarize Mass program run by the Massachusetts Clean Energy Center (MassCEC) | AEC | 1-3 | MA Clean Energy Center and MA Department of Energy Resources (DOER) Solarize Massachusetts programs
| Strategy 4.2: Identify good places for municipal solar projects | AEC, TP | Ongoing
| Strategy 4.3: Consider participation in Green Municipal Aggregation program on behalf of Town’s residents | AEC | 4-6 | MAPC’s Municipal Aggregation Toolkit and municipal aggregation program, Community Electricity Aggregation PLUS
| Strategy 4.4: Consider adding language into zoning code to explicitly allow for rooftop solar arrays | AEC, TP | 4-6
Goal 5: Reduce vehicle fuel use, support transition to Evs
| Strategy 5.1: Install electric vehicle (EV) charging infrastructure in all municipal & school parking lots and consider purchasing additional EVs or hybrid vehicles for the Town, including the Police Department. | Cap, BOS, DPW | 7+
| Strategy 5.2: Implement a community-wide anti-idling policy | BOS | 1-3
Open Space & Recreation
Goal 1: Make protection of open space and the character of the town a priority in all townwide land use decisions, in keeping with citizens’ wishes, to preserve access and scenic beauty
| Strategy 1.1: Develop and maintain a list and priorities of properties suitable for potential acquisition on conservation by the Town and make recommendations | OSRC, BoA, BOS, TP | Ongoing | LAND, CPA
Goal 2: Protect and maintain the natural environment
| Strategy 2.1: Create a town database of significant natural resources, wildlife habitats and corridors, rare species habitat, vernal pools, endangered plant habitat | OSRC, CC, TP, Eng | Ongoing
| Strategy 2.2: Revive or expand implementation of Water Dept.’s Rain Garden Program | WD, OSRC | Ongoing
| Strategy 2.3: Support the restoration of shellfish beds, including developing an Inter- Municipal Agreement with the Town of Scituate to reduce phosphate pollution into the Gulf River | SW, HC, CC, BOS, Town of Scituate | Ongoing
| Strategy 2.4: Consider bylaw and regulatory changes to prohibit phosphate and nitrategenerating uses along Gulf River and other tributaries to the Harbor, Straits Pond, and along other sensitive bodies of water or wetlands areas and their tributaries | HC, CC, OSRC, BOH | 4-6
| Strategy 2.5: Consider reviving plan for ocean outfall for sewer system to reduce fresh water incursion into the Harbor | SC, BOS | 4-6
| Strategy 2.6: Organize selective non-toxic eradication programs of invasive species where appropriate | OSRC, CC, DPW | Ongoing
| Strategy 2.7: Work to protect Town water supplies | WD | Ongoing
Goal 3: Improve recreational opportunity and access
| Strategy 3.1: Study the feasibility of “shared road” bikeways, walkways and sidewalks with proper signage for vehicular traffic | RC, DPW, TP | Ongoing | Chpt. 90, Mass Trails Grant, MAPC Landline, MAPC Trail Implementation Toolkit
| Strategy 3.2: Study creation of additional walking trails on public and publicly-accessible private conservation properties | RC, CC, OSRC, Eng | Ongoing | CPA, PARC, Mass Trails Grant, MAPC Landline, MAPC Trail Implementation Toolkit
| Strategy 3.3: Continue to monitor the need for development of new ball fields and play areas throughout town, and act upon opportunities as they present themselves | RC | Ongoing | CPA, PARC
| Strategy 3.4: Improve access to our waterways, including our harbors, ponds, ocean front, launching ramps and mooring areas | RC, HM, Har | Ongoing
| Strategy 3.5: Increase town recreational operated programs for all ages | OSRC, RC | Ongoing
| Strategy 3.6: Work cooperatively with the Department of Conservation and Recreation, The Trustees of Reservations, Cohasset Conservation Trust and any other non-town owner of publicly-accessible open space. | OSRC | Ongoing
Public Health
Goal 1: Sustain and expand access to locally produced and healthy foods in town
| Strategy 1.1: Continue support and identify expansion opportunities for the farmers market to encourage use of local and healthy foods (e.g., Holly Hill) | BOH | Ongoing
| Strategy 1.2: Develop and implement a Community Food System Action to help preserve existing agricultural uses and soils, use of marine resources, and respond to climate driven issues that could affect local food production | BOH, BOS | 4-6
| Strategy 1.3: Monitor local needs for supplemental nutrition benefits, especially among vulnerable populations including low income households and seniors | BOH, EA | Ongoing
Goal 2: Sustain support for actions to monitor and respond to issue relates to the mental and emotional wellness of residents, particularly that of youth and older adults
| Strategy 2.1: Conduct an annual town-wide communications campaign to reduce the perception of stigma for receiving mental and emotional support | SHCC | Ongoing
| Strategy 2.2: Continue to support programs that provide social and emotional support to younger and older residents | SHCC, EA | Ongoing
| Strategy 2.3: Support the development of a teen or intergenerational center in town | SHCC | Ongoing
| Strategy 2.4: Conduct regular (annual or bi-annual) town-wide surveys to gather information about parents’ behaviors in relation to their children and youth in town (e.g., social host law, conversation with children about substance use) | SHCC | Ongoing
Goal 3: Prioritize active transportation (walking, biking, and transit use) and open space access to promote physical activity and exposure to outdoor natural environments
| Strategy 3.1: Sustain and expand local programming for activities that include physical activity | RC | Ongoing
Goal 4: Addresses environment hazards to reduce resident exposure to substances that reduce the quality of life in town
| Strategy 4.1: Develop and disseminate information about prevention and reduction of tick and mosquito exposure | BOH | Ongoing
| Strategy 4.2: Provide informational materials for new and existing residents who live in proximity to roadways with higher traffic volumes (e.g., Route 3A) | BOH | Ongoing
| Strategy 4.3: Prioritize actions that reduce local single occupant vehicle trips in order to reduce locally-generated motor vehicle trips and related air pollutants | TP, AEC | Ongoing
| Strategy 4.4: Provide more mobility options for older residents and households with limited access to personal vehicles in order to enhance transportation safety, connect with local destinations and maintain community connections | EA | Ongoing
| Strategy 4.5: Explore current risks associated with Wampatuck Park’s former military uses and where necessary, update information (e.g., signage) for park users so that they are aware of potential exposures | BOH, OSRC | Ongoing
Goal 5: Assess potential health impacts of proposed projects and policies by integrating a health and equity lens into local decision-making
| Strategy 5.1: Use a health assessment tool, such as the NACCHO Public Health in Land Use Planning & Community Design checklist, in planning and development decision making | TP, PB | Ongoing
| Strategy 5.2: Bring health perspective the Community Preservation Committee through consultation with the Health Department or Board of Health | BOH, CPC | Ongoing
| Strategy 5.3: Explore use of Racial Equity Impact Assessment in municipal planning and development decision making | TP, PB | Ongoing
Historical & Cultural Resources
Goal 1: Preserve the historic residential character of Cohasset
| Strategy 1.1: Celebrate the Town's comprehensive historical record | HC, TP | Ongoing
| Strategy 1.2: Establish vision and priorities to guide historic preservation planning efforts | HC, TP | 1-3 | MA Historical Commission
| Strategy 1.3: Strengthen the Local Historic District Commission with the adoption of additional bylaws such as an Affirmative Maintenance Bylaw | CCHDC, TP, PB | 4-6 | MA Historical Commission
| Strategy 1.4: Establish a Demolition Delay Bylaw | TP, HC, PB | 1-3 | MA Historical Commission
| Strategy 1.5: Explore the expansion of the Local Historic District | CCHDC | 4-6 | MA Historical Commission
Goal 2: Develop additional local capacity to manage and enhance historic and cultural resources
| Strategy 2.1: Expand partnerships among historic and cultural organizations through development of a Historic Preservation Plan | HC, TP | 4-6 | CPA
| Strategy 2.2: Implement new partnerships among organizations within historic and cultural asset clusters for programming, maintenance, fundraising and promotion | HC | Ongoing
| Strategy 2.3: Establish programs such as land alteration management to prevent clear cutting and the alteration of natural rock ledges | TP, PB | 4-6
| Strategy 2.4: Expand Design Review Board purview to include residential properties | TP, PB | 1-3
Goal 3: Enhance Cohasset’s historic and cultural resources
| Strategy 3.1: Revitalize and restore Town Common to historic standards | HC | 7+ | CPA, MPPF
| Strategy 3.2: Continue Community Preservation Act (CPA) funding for maintenance and restoration of historic properties | CPC, HC | Ongoing | CPA. MPPF
| Strategy 3.3: Provide best practices information through the Town’s Historical Commission about how to research house histories | HC, HS | Ongoing | MA Historical Commission Survey and Planning Grants
| Strategy 3.4: Review zoning in Cohasset Common Historic District | TP, PB | 1-3
| Strategy 3.5: Highlight historic and cultural resources during annual cultural events | HC, HS | Ongoing | MA Cultural Council
Goal 4: Enhance creative and cultural economic development
| Strategy 4.1: Celebrate the upcoming 250th anniversary by highlighting local cultural and historic resources | 250, HC, HS, BOS | 1-3
| Strategy 4.2: Explore economic development strategies that highlight local artists and food producers | TP, BOH, CoC | Ongoing
| Strategy 4.3: Develop a process to establish a cultural district | TP | 4-6
| Strategy 4.4: Commemorate notable historic achievements | HC | Ongoing
Land Use
Goal 1: Plan and invest strategically for smart growth in order to preserve Cohasset’s community character
| Strategy 1.1: Complete study of Cohasset residential land use patterns | TP, PB | 1-3
| Strategy 1.2: Review existing zoning bylaw on accessory dwelling units (ADUs) | TP, PB, AHSC | 1-3
| Strategy 1.3: Review zoning bylaw to allow greater housing options in certain areas along Rt. 3A and near the train station (see Housing chapter) | TP, PB, AHSC | 1-3
| Strategy 1.4: Review and revise the zoning bylaw to ensure desired smart growth and enforcement of zoning bylaws | TP, PB, B&I, ZBA | 1-3
| Strategy 1.5: Improve planning and permitting process by educating community through zoning clinics | TP, PB, ZBA | Ongoing
Goal 2: Revitalize the Harbor area in accordance with the Harbor Plan vision and landside development and infrastructure recommendations
| Strategy 2.1: Support public use of and access to the Harbor | Har, HM | Ongoing
| Strategy 2.2: Identify and plan for appropriate improvements to landside and waterside infrastructure | Har, HM | 7+
| Strategy 2.3: Improve the interconnectivity between the Village and the Harbor | TP, Har, DPW, CoC | Ongoing
| Strategy 2.4: Explore zoning changes to the Harbor to reflect the goals of the Harbor Plan and the demand for alternative uses along the water’s edge | TP, PB | 1-3
Goal 3: Protect open space in all town-wide land use decisions in order to preserve access and scenic beauty in accordance with the OSRP
| Strategy 3.1: Develop a set of criteria for ranking and evaluation of future open space acquisitions by the Town | OSRC, CC, TP | 1-3
| Strategy 3.2: Develop and maintain a list and priorities of properties suitable for potential acquisition on conservation by the Town and make recommendations | OSRC, BoA, BOS, TP | Ongoing | LAND, CPA
| Strategy 3.3: Request comment from the OSRC on permitting and land acquisition and disposition matters before the land use permitting boards, Board of Selectmen and Town Meeting | PB, OSRC | Ongoing
| Strategy 3.4: Increase public awareness of tax incentives available to private landowners who preserve open space | BoA, OSRC, BOS | Ongoing
| Strategy 3.5: Increase public outreach on the value and importance of open space, including the benefits of public-private partnerships dedicated to preserving and enhancing open space. | OSRC | Ongoing
Goal 4: Attract and retain diverse business in Cohasset while retaining small town character
| Strategy 4.1: Develop plans for joint economic development of the Harbor area and the Village | TP, Har, CoC | 4-6 | MA Downtown Initiative
| Strategy 4.2: Complete study of commercial build-out analysis including impact of potential regional sewer on economic development along Rt. 3A | TP, SC | 4-6
| Strategy 4.3: Establish design guidelines that can be adopted for the Route 3A corridor | TP, PB | 1-3
| Strategy 4.4: Consider ways in which to introduce more housing in Cohasset Village as a way to enhance market opportunities in that district (see Economic Development chapter) | TP, PB | 7+ | MA Downtown Initiative
Economic Development
Goal 1: Create a variety of economic activities in town to satisfy citizen’s desires for more varied experiences in the Village, the Harbor and along the commercial corridor of Route 3A
| Strategy 1.1: Increase density in the Village by building more mixed-use developments | TP, PB | 4-6 | MA Downtown Initiative
| Strategy 1.2: Pursue development of a Cohasset Cultural District through the Massachusetts Cultural Council | TP | 4-6 | MA Cultural Council
| Strategy 1.3: Create a Village-Harbor Vision | TP, Har | 1-3 | MA Downtown Initiative
Goal 2: Reimagine the Town’s Engagement with Economic Development
| Strategy 2.1: Develop a comprehensive economic development plan that melds the Town's sites of economic and social activity into a broader framework | TP | 1-3
| Strategy 2.2: Rejuvenate the Economic Development Committee (EDC) to implement this plan | BOS | 1-3
| Strategy 2.3: The EDC should develop working relationships with local, state and regional entities to provide resources and technical assistance to enhance the Town's economic base | CoC, DBTA | 1-3
Goal 3: Strengthen the traditional economic development organizations including the Cohasset Chamber of Commerce and the local Downtown Business Association (DTBA)
| Strategy 3.1: Broaden public knowledge of Cohasset's environmental, historical, and community assets by connecting with regional organizations such as the Greater Boston Convention & Visitors Bureau | CoC, DBTA | 1-3
Goal 4: Increase the number of visitors traveling to Cohasset for enjoyment and to use the Town's resources
| Strategy 4.1: Identify ways of increasing access to town by improving connections between public transit and the Village | TP, MBTA | Ongoing
| Strategy 4.2: Connect the Village and the Harbor | TP, Har, DPW | Ongoing
| Strategy 4.3: Create partnerships with surrounding seaside towns to connect tourism-related activities | CoC, DBTA | Ongoing
Goal 5: Implement the economic development recommendations of the Master Plan and the Harbor Plan, focusing on the greatest strengths of businesses that operate formal and informal establishments, including in-home enterprises
| Strategy 5.1: Identify a location where an in-Village collaborative workspace can attract and serve business professionals | CoC, DBTA | Ongoing
| Strategy 5.2: Engage Village banking institutions to serve as financial intermediaries and sources of business planning advice | CoC, DBTA | Ongoing
| Strategy 5.3: Increase new business formation by identifying complementary activities that match the needs of existing businesses | CoC, DBTA | Ongoing
| Strategy 5.4: Harness local goodwill by developing strong brand recognition of locally produced goods and services | CoC, DBTA | Ongoing
| Strategy 5.5: Streamline the steps required to start and sustain a new business | BOS | 1-3
| Strategy 5.6: Support and where appropriate create water-based economic activities including recreation, commercial, and civic functions. Develop resources to support the continued operation and development of the Cohasset fishing industry | Har, HM, OSRC | 7+