## Implementation Matrix
|  | Strategies |  |  | Responsible Entities | [5 empty] | Funding Opportunities | [6 empty] | Logistics |  | Examples/Case Studies
Core Theme | G O A L | Strategy Code | Strategy Narrative | Strategy Type | Town Department (Lead) | Town Department (Support) | Town Board/ Committee (Lead) | Town Board/ Committee (Support) | Local Organization (Support) | Additional Partners | Municipal Funding Source Opportunities | State Funding Source Opportunities | State Funding Source Opportunities 2 | State Funding Source Opportunities 3 | State Funding Source Opportunities 4 | Federal Funding Source Opportunities | Non-Profit Funding Source Opportunities | Approximate Cost | Timing | Link 1 | Link 2 | Link 3 | Link 4
Core Theme 1 | A | 1.A1 | Consider amending the Open Space Residential Design bylaw to align with the Open Space Design / Natural Resource Protection Zoning model bylaw. | Regulatory & Policy | Planning and Zoning Admin | Town Administrator | Planning Board | Open Space Committee |  |  |  | EEA Planning Assistance Grant | MAPC technical assistance | Community Planning Grant |  |  |  | $ = less than $50k | Medium-Term (4-7 years) | Model Bylaw | Wellesley, MA | Ashby, MA | Presentation
Core Theme 1 | A | 1.A2 | Provide guidelines for and education on installing and maintaining sustainable landscapes on public and private lands, for example, through the Greenscapes North Shore Coalition’s guidelines or other readily available resources (see also the Water Conservation Plan 2007). | Regulatory & Policy | Planning and Zoning Admin | DPW | Planning Board | Sustainability Committee | Topsfield Garden Club |  |  | MAPC |  |  |  |  | Barr Association | $ = less than $50k | Long-Term (8-10+ years) | Concord, MA | Greenscapes North Shore Coalition "Your Yard"
Core Theme 1 | A | 1.A3 | Increase involvement with regional collaborations (e.g., Ipswich River Watershed Association) to help meet common water quality, groundwater protection, and stormwater management goals and objectives (see the Water Conservation Plan 2007). | Capacity Building | Storm Water Coordinator | MS4 Coordinator | Planning Board | Conservation | Ipswich River Watershed Association | Department of Public Works (Water) | [6 empty] | Ipswich River Water Association community services | $ = less than $50k | Short-Term (0-3 years) | Ipswich River Watershed Association
Core Theme 1 | A | 1.A4 | Develop a specific policy, process, and priority list by which the Town determines whether to exercise its right of first refusal under Chapter 61. | Regulatory & Policy | Town Administrator | Planning and Zoning Admin | Planning Board | Open Space Committee |  | Agricultural Commission; Select Board | Town Counsel services | [6 empty] | $ = less than $50k | Short-Term (0-3 years) | Wenham, MA | Chapter 61
Core Theme 1 | A | 1.A5 | Use grants and other funding mechanisms to purchase conservation restrictions or acquire prioritized high-value conservation land designated on the Town’s priority list, especially properties that abut existing open space and recreational land. The Town could also partner with a regional land trust on acquisition or holding conservation restrictions. | Design, Physical, & Acquisition | Conservation | Town Administrator | Select Board | Finance Committee | Essex Country Greenbelt |  |  | Conservation Partnership Grant Program | Landscape Partnership Grant Program | LAND Grant | Agricultural Preservation Restriction Program | Land and Water Conservation Fund Grant |  | $$$$ = $1m+ | Long-Term (8-10+ years) | Transfer of Development Rights (TDR) program | Land and Recreation Grants and Loans | Essex County Greenbelt land conservation options | Agricultural Preservation Restriction program
Core Theme 1 | B | 1.B1 | Collaborate and support revising and resurrecting the existing Historical Commission’s self-guided historic walking route centered around the Town Center, share it via the website, make paper copies available, and create a virtual town-wide tour. | Programmatic | Town Administrator | Planning and Zoning Admin | Historical Commission | Economic and Community Development Committee | Topsfield Historical Society | Speical Projects; Communications Director; Recreation; Library | Local Cultural Council | [6 empty] | $ = less than $50k | Medium-Term (4-7 years) | Salem Witch Trials Online Tour | Maynard Historic Walking Tours | Topsfield Existing Historic District Tour
Core Theme 1 | B | 1.B2 | Identify, assess, and prioritize areas for new local historic districts, including the potential for a floating district to protect thematic resources that are not co-located. | Regulatory & Policy | Town Administrator | Planning and Zoning Admin | Historical Commission | Planning Board | Topsfield Historical Society |  |  | Massachusetts Historical Commission Survey and Planning Grant Program | [5 empty] | $ = less than $50k | Medium-Term (4-7 years) | Establishing Local Historic Districts | Floating district | Medway Master Plan report | Massachusetts Historical Commission Survey and Planning grant program
Core Theme 1 | B | 1.B3 | Identify possible incentives for private property owners to invest in and maintain historic structures and educate private property owners of historic structures about existing incentives. | Regulatory & Policy | Town Administrator | Planning and Zoning Admin | Historical Commission |  | Topsfield Historical Society | Board of Assessors |  | Massachusetts Preservation Projects Fund |  |  |  | Federal and state tax credits | Preservation restrictions (federal income tax deduction if donation) | $$ = $50k-$250k | Long-Term (8-10+ years) | Bedford, MA | Massachusetts Preservation Projects fund | Massachusetts Historic Preservation matching grants | Massachusetts Historic Rehabilitation Tax Credit
Core Theme 1 | B | 1.B4 | Continue partnerships with the Topsfield Historic Commission, Friends of the Topsfield Library, and Topsfield Historical Society to build public knowledge and tourism base for of historical figures and events (e.g., Salem witch trials, religious history, indigenous history, agricultural history, etc.). | Capacity Building | Town Administrator | Public Library | Historic Commission | Economic and Community Development Committee | Topsfield Historical Society | Topsfield Public Library; Board of Library Trustees; Recreation | Local Cultural Council funds | [5 empty] | Friends of the Topsfield Library | $ = less than $50k | Short-Term (0-3 years) | Mass Humanities grants | Topsfield Cultural Council grants
Core Theme 1 | B | 1.B5 | Explore opportunities to install appropriate wayfinding signage, especially in the Historic District. | Design, Physical, & Acquisition | Town Administrator | Department of Public Works | Historical Commission | Economic and Community Development Committee | Topsfield Historical Society |  | Local Cultural Council funds | MHC Survey and Planning Grant | [5 empty] | $ = less than $50k | Short-Term (0-3 years) | Ipswich, MA | Wayfinding signage definition
Core Theme 1 | C | 1.C1 | Seek grants to incentivize private water storage and groundwater recharge through a no/low-cost rain barrel program. | Programmatic | Department of Public Works (Water) | Town Administrator | Sustainability Committee | Select Board |  | Conservation | Bought at cost, and sold to residents for net zero cost | [6 empty] | $ = less than $50k | Short-Term (0-3 years) | Great American Rain Barrel Co. | Newburyport, MA | State rain barrel program
Core Theme 1 | C | 1.C2 | Educate the public on sustainability and resiliency topics, such as water conservation in tandem with their water bills, renewable energy options, and solid waste management. | Programmatic | Town Administrator | Department of Public Works (Water) | Sustainability Committee | [9 empty] | Ipswich River Watershed Association Community Services | $ = less than $50k | Short-Term (0-3 years) | Winchester, MA | Ipswich River Watershed Association
Core Theme 1 | C | 1.C3 | Establish a Solid Waste Advisory Committee to evaluate new services, expand existing services, and educate residents about programs that improve recycling rates, encourage composting, and reduce the amount of waste being landfilled. Examples might be to expand bi-weekly recycling to weekly pickup and set up a “swap shed” where residents can exchange unwanted, still-usable items. | Capacity Building | Town Administrator | Department of Public Works | Sustainability Committee | Select Board |  | Board of Health |  | Sustainable Materials Recovery Program Municipal Grant and Technical Assistance | Sustainable Materials Recovery Program (SMRP) Municipal Grant | MassDEP Reduce, Reuse, Repair Micro-Grant |  |  |  | $$ = $50k-$250k | Medium-Term (4-7 years) | Falmouth, MA | Composting (Mass.gov) | Swap shop (Mass.gov) | Yarmouth, MA
Core Theme 2 | A | 2.A1 | Update the Topsfield Complete Streets Prioritization Plan to identify what has already been accomplished and where to prioritize investment in biking infrastructure around the Town, such as bike parking at municipal facilities and open spaces, public repair stations in strategic locations, and bike lanes along major thoroughfares. | Regulatory & Policy | Department of Public Works | Town Administrator | Traffic Advisory Committee | Select Board |  | Special Projects; Rail Trail Committee |  | Rural Development Fund | Safe Routes to Schools | Transportation Improvement Program (TIP) | Shared Streets and Spaces Grant | Chapter 90 |  | $ = less than $50k | Short-Term (0-3 years) | Arlington, MA Sept. 2023 Update | Topsfield Complete Streets Prioritization Plan | Public repair stations tutorial
Core Theme 2 | A | 2.A2 | Update the Topsfield Complete Streets Prioritization Plan to identify what has already been accomplished and where to prioritize infrastructure improvements at key intersections, such as Route 1 and Route 97, Route 97 and Main Street, Central Street and Route 1, and Washington Street and Boxford Road. | Regulatory & Policy | Department of Public Works (Highway) | Town Administrator | Traffic Advisory Committee | Select Board |  | Special Projects |  | Rural Development Fund | Complete Streets Funding Program | Transportation Improvement Program (TIP) | Massworks | Chapter 90 |  | $ = less than $50k | Short-Term (0-3 years) | Watertown, MA 2023 Update | Topsfield Complete Streets Prioritization Plan
Core Theme 2 | A | 2.A3 | Update the Topsfield Complete Streets Prioritization Plan to identify what has already been accomplished and where to prioritize pedestrian access across the Town, such as Town facilities, school buildings, open spaces, and major thoroughfares. | Regulatory & Policy | Department of Public Works | Town Administrator | Traffic Advisory Committee | Select Board |  | Special Projects |  | Rural Development Fund | Safe Routes to Schools | Transportation Improvement Program (TIP) | Shared Streets and Spaces Grant | Chapter 90 |  | $ = less than $50k | Short-Term (0-3 years) | Complete Streets Funding | North Reading, MA | Topsfield Complete Streets Prioritization Plan
Core Theme 2 | A | 2.A4 | Conduct an ADA audit of key corridors in town and the Rail Trail to identify locations needing improvements, such as curb ramps, crosswalks, and accessible pedestrian signals. | Regulatory & Policy | ADA Coordinator | Department of Public Works | Traffic Advisory Committee | Rail Trail Committee |  |  |  | Rural Development Fund | Complete Streets Funding Program | Transportation Improvement Program (TIP) | ADA Improvement grants | Chapter 90 |  | $$ = $50k-$250k | Medium-Term (4-7 years) | New Marlbourough, MA | Topsfield Complete Streets Prioritization Plan | Westford Road Safety audit (with ADA recommendations)
Core Theme 2 | B | 2.B1 | Encourage the development of multi-family, non-age restricted housing in the Business Village, Business Highway, Business Highway North, and Business Park Districts through existing and newly proposed zoning and a new MBTA district. | Regulatory & Policy | Town Administrator | Planning and Zoning Admin | Planning Board | Zoning Board of Appeals | Topsfield Community Partnership |  |  | EEA Planning Assistance Grants | Rural Development Fund |  |  |  | Citizen Planner Training Collaborative | $ = less than $50k | Short-Term (0-3 years) | MBTA district requirements
Core Theme 2 | B | 2.B2 | Establish a Housing Advisory Committee. The Housing Advisory Committee could advocate for zoning changes in response to housing needs, improve town capacity to implement housing strategies and policies, build public and political support for Topsfield's housing goals, do community outreach and education, and foster partnerships with regional housing organizations. | Capacity Building | Town Administrator | Planning and Zoning Admin | Select Board | Planning Board |  | Future Housing Advisory Committee | Volunteer | [6 empty] | $ = less than $50k | Short-Term (0-3 years) | Housing Toolbox for MA Communities | Groveland, MA Affordable Housing Committee | Orleans, MA Affordable Housing Committee | Ayer, MA Affordable Housing Committee
Core Theme 2 | B | 2.B3 | Seek funding and a consultant to create a housing plan to analyze housing needs, evaluate the market feasibility and impacts of zoning changes, and work with the Town to identify other regulatory, programmatic, coordination, and capacity strategies. | Regulatory & Policy | Town Administrator | Planning and Zoning Admin | Planning Board | Select Board |  | Future Housing Advisory Committee |  | Rural Development Fund | Community Planning Grant Program |  |  |  |  | $$ = $50k-$250k | Medium-Term (4-7 years) | Ipswich, MA HPP | Orleans, MA Ten-Year Housing Plan
Core Theme 2 | C | 2.C1 | Explore options to reinstate the Topsfield Park and Ride bus service to offer options to local commuter rail stations and/or commuting into Boston. | Capacity Building | Town Administrator |  | Select Board | Economic and Community Development Committee | Massachusetts Department of Transportation |  |  | Community Transit Grant Program | Efficiency and Regionalization Grant PRogram | Community Connections grant | Regional Transit Innovation Grant | Mobility Assistance Program |  | $$$ = $250k-$1m | Medium-Term (4-7 years) | Topsfield Park and Ride bus service
Core Theme 2 | C | 2.C2 | Collaborate with the RMV to host regular Older Adult safe driving workshops for residents and caregivers to extend independent living options for older adults and reduce related crashes in Town. | Capacity Building | Council on Aging |  | Council on Aging | Registry of Motor Vehicles | Council on Aging (COA) |  |  | Heping Hands Mini-Grants | [5 empty] | $ = less than $50k | Medium-Term (4-7 years) | RMV Safe Driving Courses | Older Adult safe driving workshops | MassDOT: Crash Data Portal (Must select Topsfield)
Core Theme 2 | C | 2.C3 | Seek funding opportunities to expand the Council on Aging shuttle bus capacity, service routes, vehicle type, adding lift-assists, and ridership requirements. | Capacity Building | Council on Aging | Town Administrator | Council on Aging | Council on Aging (COA) |  |  |  | MAPC Taxicab, Livery, and Hackney Transporation Partnership Grants Program | Community Connections Grant |  |  | Mobility ASsistance PRogram |  | $$ = $50k-$250k | Medium-Term (4-7 years) | Council on Aging shuttle bus | Wellesley, MA | Waltham, MA
Core Theme 2 | C | 2.C4 | Investigate the potential use of Council on Aging vehicle(s) for on-demand shuttle use during off hours. | Capacity Building | Council on Aging | Town Administrator | Council on Aging | Council on Aging (COA) |  |  |  | Community Transit Grant Program | Efficiency and Regionalization Grant Program | Community Connections Grant |  |  |  | $$ = $50k-$250k | Long-Term (8-10+ years) | On-demand service | Marshfield GATRA | Acton, MA
Core Theme 3 | A | 3.A1 | Regularly review and update zoning downtown and in commercial areas on Route 1 to be conducive to development by allowing more by-right target industries as new commercial uses arise. | Regulatory & Policy | Town Administrator | Planning and Zoning Admin | Planning Board | Economic and Community Development Committee |  |  |  | Rural Development Fund | EEA Planning Grants | Community Planning Grant Program |  |  |  | $ = less than $50k | Short-Term (0-3 years) | Topsfield Zoning Bylaw Table of Use Regulations
Core Theme 3 | A | 3.A2 | Capitalize on residents’ overwhelming support for increased business activity by advancing market-ready economic development opportunities. | Programmatic | Town Administrator | Planning and Zoning Admin | Economic and Community Development Committee |  |  |  |  | Community Planning Grant Program | Community One Stop for Growth |  |  |  |  | $ = less than $50k | Short-Term (0-3 years) | Former Highway Garage Building | --- | Community One Stop for Growth
Core Theme 3 | A | 3.A3 | Encourage and incentivize the development of a restaurant or pub in the downtown area to enhance the vibrancy and build community through actively seeking out innovative and creative programs as well as formal paths such as federal and state grants. | Programmatic | Town Administrator |  | Select Board | Economic and Community Development Committee |  | Finance Committee | Local property tax incentive (TIF) | Rural Development Fund | Pubic Surplus Property Project |  |  |  |  | $$ = $50k-$250k | Short-Term (0-3 years) | Downtown Revitilization Plan
Core Theme 3 | A | 3.A4 | Continue to invest in beautification and placemaking initiatives downtown to attract residents and visitors, through ongoing stewardship of existing amenities, and new placemaking initiatives as maintenance capacity allows. | Design, Physical, & Acquisition | Town Administrator | Department of Public Works | Economic and Community Development Committee | Select Board | Topsfield Community Partnership |  |  | MassDOT Complete Streets | Shared Streets and Spaces |  |  |  |  | $ = less than $50k | Short-Term (0-3 years) | Solar street lights | Shared Streets and Spaces Grant Program
Core Theme 3 | A | 3.A5 | Explore opportunities to expand wastewater infrastructure capacity downtown. | Design, Physical, & Acquisition | Town Administrator | Department of Public Works | Select Board | Board of Health |  |  |  | State Revolving Fund (SRF) Loan Program | MassWorks | Rural Development Fund | HousingWorks Infrastructure Program |  |  | $$$$ = $1m+ | Medium-Term (4-7 years) | Massachusetts Water Resources Grants & Financial Assistance | U.S. EPA Funding Sources for Small and Rural Wastewater Systems
Core Theme 3 | A | 3.A6 | Investigate options for design guidelines for Topsfield's commercial districts or modify the site plan review standards to ensure new development is compatible with the Town, as a part of the site plan review process. | Regulatory & Policy | Planning and Zoning Admin | Town Administrator | Planning Board | Zoning Board of Appeals |  |  |  | MA Downtown Initiative Program | [5 empty] | $ = less than $50k | Short-Term (0-3 years) | Watertown, MA | Mendon, MA Design Guidelines | design guidelines
Core Theme 3 | B | 3.B1 | Work proactively with existing landowners to support the redevelopment of vacant or underutilized properties on Route 1. | Programmatic | Town Administrator |  | Economic and Community Development Committee | Select Board |  |  |  | MassDev Site Readiness Program | MassDev Underutilized Properties |  |  |  |  | $ = less than $50k | Medium-Term (4-7 years) | Community Development Finance Institutions | Community One Stop for Growth | Redevelopment of Obsolete Land Uses in Your Community
Core Theme 3 | B | 3.B2 | Support existing business retention and expansion through open communication and coordination with business owners. | Programmatic | Town Administrator |  | Economic and Community Development Committee | Select Board |  |  | Topsfield operating budget | Small Business Technical Assistance Program |  |  |  |  | Small Business Development Center Network | $ = less than $50k | Short-Term (0-3 years) | Tips for Business Retention & Expansion
Core Theme 3 | C | 3.C1 | Explore hiring a Community Development Director or Town Planner to support small businesses, take advantage of economic development opportunities (e.g., financing incentives, grants, etc.), and develop a marketing strategy for attracting new business that aligns with the Town’s vision and goals. | Capacity Building | Town Administrator | Building Inspector/ Zoning Enforcement Officer | Select Board | Economic and Community Development Committee |  |  | Town operating budget | [6 empty] | $$ = $50k-$250k | Short-Term (0-3 years) | Somerset, MA Town Planner Description
Core Theme 3 | C | 3.C2 | Develop and communicate clear and standardized guidelines and procedures for prospective entrepreneurs, including a point-person to speak with at the Town and user-friendly website interfaces (contingent on additional Town capacity). | Regulatory & Policy | Town Administrator | Planning and Zoning Admin | Economic and Community Development Committee | Zoning Board of Appeals |  | Building Inspector | Town operating budget | [6 empty] | $ = less than $50k | Short-Term (0-3 years) | New Bedford EDC | Andover, MA Business Resource Guide
Core Theme 3 | C | 3.C3 | Expand awareness of volunteer opportunities and strengthen community partnerships related to economic development and entrepreneurship (Topsfield Community Partnership). | Capacity Building | Town Administrator | Digital Communication Coordinator | Economic and Community Development Committee | Select Board | Topsfield Community Partnership | [7 empty] | Topsfield Community Partnership | $ = less than $50k | Short-Term (0-3 years) | Topsfield Community Partnership) | Community One Stop for Growth
Core Theme 3 | C | 3.C4 | Cultivate strong working relationships between the Town and key businesses/ economic development players, either formally (i.e., through a local or regional Business Chamber) or informally through open communication and mutual respect. | Capacity Building | Town Administrator |  | Economic and Community Development Committee | Select Board | Topsfield Community Partnership | [8 empty] | $ = less than $50k | Medium-Term (4-7 years) | Business Chamber
Core Theme 3 | C | 3.C5 | Continue to support and promote small businesses and local farms, including events showcasing local businesses. | Programmatic | Town Administrator | Recreation | Economic and Community Development Committee | Select Board | Topsfield Community Partnership | [7 empty] | Topsfield Community Partnership | $$ = $50k-$250k | Short-Term (0-3 years) | Hudson, MA events page | Grow Food Northampton | Topsfield, MA Business Development Showcase
Core Theme 4 | A | 4.A1 | Explore opportunities to expand the Recreation Department's capacity through a Community Development Director and/or Recreation Director. | Capacity Building | Town Administrator | Recreation | Select Board | Finance Committee |  |  | Town operating budget | [6 empty] | $$ = $50k-$250k | Medium-Term (4-7 years) | Recreation Director.
Core Theme 4 | A | 4.A2 | Continue supporting and collaborating with local groups to offer historical and cultural education-based events for residents and promote volunteerism in the community, for example through the Topsfield Public Library, the Historical Society, the Parent Teacher Association Organization (TESPTO), the TriTown Council, Cultural Council, and Council on Aging. | Programmatic | Council on Aging | Public Library | Historic Commission | Cultural Council | Topsfield Historical Society | Tri-Town Council | Local cultural council | MHC planning grant |  |  |  |  | Friends of the Public library | $$ = $50k-$250k | Short-Term (0-3 years) | Amherst, MA | Massachusetts Service Alliance
Core Theme 4 | A | 4.A3 | Continue to host community events for residents and visitors near the Town Center and Town Common area, such as the Holiday on the Green and HomeGrown Market. | Programmatic | Recreation | Town Administrator | Agricultural Commission | Cultural Council | Topsfield Community Partnership |  | Local Cultural Council | [5 empty] | Historic Society | $$ = $50k-$250k | Short-Term (0-3 years) | Topsfield Events
Core Theme 4 | A | 4.A4 | Continue to explore intergenerational programs to connect youth and young adults with older adults. | Programmatic | Council on Aging | School Departmentss | Council on Aging | Elementary and Masconomet School Committees |  | Recreation | Local Cultural Council | [5 empty] | Friends of the Public library | $$ = $50k-$250k | Medium-Term (4-7 years) | Holden, MA | intergenerational programs
Core Theme 4 | A | 4.A5 | Update and maintain a town-wide online shared event coordination calendar. | Programmatic | Recreation | Digital Communication Coordinator | Economic and Community Development Committee | Council on Aging | Topsfield Community Partnership
Core Theme 4 | B | 4.B1 | Expand Topsfield Top 10 Newsletter to proactively market upcoming events and opportunities in Town. | Programmatic | Digital Communication Coordinator | Town Administrator | Select Board |  |  |  | Town operating budget | [6 empty] | $ = less than $50k | Short-Term (0-3 years)
Core Theme 4 | B | 4.B2 | Continue to advance the use of electronic applications for permit submittal and review. | Programmatic | Building & Zoning Enforcement Ofificer | Town Administrator | Select Board |  |  | Special Projects; All Permitting Department Heads |  | Community Compact IT Grant | [5 empty] | $$ = $50k-$250k | Short-Term (0-3 years) | Mashpee, MA | Arlington, MA online permitting system announcement
Core Theme 4 | B | 4.B3 | Continue modernizing policies and implement staff training on social media as an effective communication tool. | Regulatory & Policy | Digital Communication Coordinator | Town Administrator | Select Board |  |  |  |  | Community Compact IT Grant | [5 empty] | $ = less than $50k | Short-Term (0-3 years) | Massachusetts Municipal Association Considerations for a Municipal Social Media Policy
Core Theme 4 | B | 4.B4 | Support the Town library in its goals to enable all residents access to current technologies and to provide education on how to work those technologies. | Programmatic | Public Library | Council on Aging | Board of Library Trustees | Select Board |  |  | Town operating funds | [5 empty] | Friends of the Public Library | $$ = $50k-$250k | Short-Term (0-3 years) | BPL Services | Shrewsbury Services | Topsfield, MA Strategic Plan
Core Theme 4 | B | 4.B5 | Support the schools in their goal to invest in modern teaching and learning technologies. | Programmatic | School Departments | Masconomet Regional School Departmentss | Elementary and Masconomet School Committees | Finance Committee |  |  | Town capital budget | DESE STEM Grants | [5 empty] | $$ = $50k-$250k | Short-Term (0-3 years) | Methuen, MA School Tech | Topsfield Public Schools | Masconomet Regional School District strategic planning process
Core Theme 4 | C | 4.C1 | Implement the Topsfield Open Space and Recreation Plan (OSRP 2019) through its seven-year Action Plan. | Regulatory & Policy | Recreation | Town Administrator | Open Space Committee | Select Board |  | Other partners as identified in the 2019 OSRP |  | Conservation Partnership Grant Program | Landscape Partnership Grant Program | LAND Grant | MAPC technical assistance | Land and Water Conservation Fund Grant |  | $$$ = $250k-$1m | Medium-Term (4-7 years) | Open Space Plan
Core Theme 4 | C | 4.C2 | Increase Town beautification efforts by identifying places for permanent and temporary public art and landscaping installations. | Design, Physical, & Acquisition | Town Administrator | Department of Public Works | Economic and Community Development Committee | Cultural Commission | Topsfield Community Parternship | Public Library | Local Cultural Council | MAPC Arts and Culture Technical Assistance | Commonwealth Places |  |  |  | Topsfield Community Partnership | $ = less than $50k | Medium-Term (4-7 years) | Topsfield Library Sculpture Program | How public art can improve quality of life | Amherst, MA Public Art Commission
Core Theme 4 | C | 4.C3 | Expand public-private partnerships to activate public and private facilities in off-hours for cultural activities and to boost indoor athletic and art-based recreation opportunities. Ideas may include the school buildings, Public Hall, library, Tri-Town Council event spaces, Emerson Center, and Topsfield Fairgrounds. | Capacity Building | Recreation Department | Public Library | Select Board | Elementary and Masconomet School Committees | Topsfield Fairgrounds |  | Town operating budget | [5 empty] | Topsfield Community Partnership | $ = less than $50k | Long-Term (8-10+ years)
Core Theme 4 | C | 4.C4 | Support ongoing efforts to create a linked trail network per the 2019 Open Space and Recreation Plan. | Design, Physical, & Acquisition | Recreation | Town Administrator | Open Space Committee | Rail Trail Committee | Friends of Topsfield Trails | Other partners as identified in the 2019 OSRP |  | Recreational Trails Program |  |  |  | Land and Water Conservation Fund Grant |  | $$$ = $250k-$1m | Long-Term (8-10+ years) | Open Space Plan
Core Theme 4 | C | 4.C5 | Consider opportunities to promote Recreational Amenities such as the new Pump Track and Pye Brook Disc Golf Course to host races and tournaments to draw tourism. | Programmatic | Recreation Department | Town Administrator | Economic and Community Development Committee | Select Board |  |  | Town operating budget | [6 empty] | $ = less than $50k | Short-Term (0-3 years) | Amesbury Pines Disc Golf Tournament | Pump Track.com
Core Theme 4 | C | 4.C6 | Create an updated ADA Transition Plan to improve access to public facilities, playgrounds, and open spaces for people with disabilities. | Regulatory & Policy | ADA Coordinator | Department of Public Works | Open Space Committee | Select Board |  |  |  | Parkland Acquisitions and Renovations for Communities (PARC) Grant | Rural Development Fund |  |  |  |  | $ = less than $50k | Medium-Term (4-7 years) | Braintree, MA | ADA Transition Plan
Core Theme 5 | A | 5.A1 | Seek grant opportunities to use green building design components in any municipal or school renovations or improvements where feasible and cost effective such as weatherization, material sourcing, indoor environmental quality, water usage, and waste management. | Capacity Building | TA/Facility Coordinator | School Departments | Sustainability Advisory Committee | Elementary and Masconomet School Committees |  | Procurement |  | Green Communities | [5 empty] | $$$ = $250k-$1m | Medium-Term (4-7 years) | Green building design (EPA.gov) | Sustainability Advisory Committee's Strategic Plan
Core Theme 5 | A | 5.A2 | Implement the recommendations in the Hazard Mitigation Plan/ Municipal Vulnerability Preparedness Plan (2021). | Regulatory & Policy | Fire/Department of Public Works | Conservation | Select Board | Finance Committee |  | Other partners as identified in the 2021 HMP/MVPP |  | Hazard Mitigation Grant Program | Municipal Vulnerability Preparedness Action Grant |  |  | Building Resilient Infrastructure and Communities (BRIC) Grant Program |  | $$$$ = $1m+ | Long-Term (8-10+ years) | Hazard Mitigation Plan
Core Theme 5 | A | 5.A3 | Continue to invest in energy-efficient equipment and facilities for municipal operations, including schools, that reduce carbon emissions, energy consumption, and costs. | Design, Physical, & Acquisition | Town Administrator | Department of Public Works | Sustainability Advisory Committee | Select Board |  | Tri-Town Schools Facility Manager; Procurement; School Committees |  | Green Communities | [5 empty] | $$$ = $250k-$1m | Short-Term (0-3 years) | Mass.gov Energy Efficiency Measures for Municipalities
Core Theme 5 | A | 5.A4 | Prioritize electric or energy-efficient municipal vehicles whenever possible as new vehicles are purchased. | Design, Physical, & Acquisition | Town Administrator | Department of Public Works, and Fire, Police | Sustainability Advisory Committee | Select Board |  | Any additional Department Managers whose departments have or acquire vehicles in the future |  | MassEVIP Fleets Incentives | Green Communities |  |  |  |  | $$ = $50k-$250k | Short-Term (0-3 years) | Energy-efficient municipal vehicles (Mass.gov)
Core Theme 5 | A | 5.A5 | Build on recent efforts, such as solar-powered streetlamps, to increase solar and other alternative energy sources at Town facilities and in Topsfield's public spaces. | Design, Physical, & Acquisition | Town Administrator | Department of Public Works | Sustainability Advisory Committee | Select Board |  | Finance Committee; Schools |  | Green Communities | [5 empty] | $$ = $50k-$250k | Medium-Term (4-7 years) | Solar-powered streetlamps | Sustainability Advisory Committee's Strategic Plan
Core Theme 5 | A | 5.A6 | Develop a greenhouse gas inventory to help understand Topsfield's baseline of significant sources of emissions, establish a greenhouse gas emission reduction goal, and document current measures taken to reduce greenhouse gas emissions. Additionally, develop an Action Plan to address gaps focusing on municipal energy reduction with high return on investment. | Regulatory & Policy | Town Administrator |  | Sustainability Advisory Committee | Select Board |  |  |  | MAPC technical assistance | [5 empty] | $ = less than $50k | Medium-Term (4-7 years) | GHG Concord, MA | Dedham, MA | Sustainability Advisory Committee's Strategic Plan | Greenhouse Gas Inventory MAPC Toolkit
Core Theme 5 | B | 5.B1 | Continue supporting all departments to compete for grants that could provide training, planning support, or funds for physical improvements to roads and facilities. | Capacity Building | Town Administrator | Department of Public Works | Select Board |  |  | Department Heads | [7 empty] | $ = less than $50k | Short-Term (0-3 years) | Grant opportunities
Core Theme 5 | B | 5.B2 | Continue to maintain and upgrade the municipal water supply infrastructure and capacity (e.g., through shared or alternative water resources such as regional planning with the Ipswich Watershed, the Salem-Beverly Water Supply Board, or MWRA). | Design, Physical, & Acquisition | Department of Public Works (Water) | Town Administrator | Select Board |  | North Shore Task Force (Sen Tarr) |  |  | Drinking Water Supply Protection Grant | Water Management Act Grant Program |  |  |  |  | $$$$ = $1m+ | Short-Term (0-3 years) | Water supply infrastructure and capacity | Ipswich Watershed | Salem-Beverly Water Supply Board | MWRA
Core Theme 5 | B | 5.B3 | Identify where different departments or cross-departmental issues may require more intensive study (e.g., public safety building feasibility study) and identify funding needed to perform those studies. | Capacity Building | Fire Department | Police Department | Select Board |  |  |  | Town operating budget | [6 empty] | $ = less than $50k | Short-Term (0-3 years) | Ashland Public Safety Building Feasability Study | Ashby, MA Public Safety Building Feasibility Study
Core Theme 5 | B | 5.B4 | Explore opportunities to enhance municipal services utilizing programs and funding opportunities from the Massachusetts Rural Policy Plan. | Capacity Building | Town Administrator |  | Select Board |  |  | Special Projects | Town operating budget | [6 empty] | $ = less than $50k | Medium-Term (4-7 years) | Rural Policy Plan
Core Theme 5 | B | 5.B5 | Support capital improvements to municipal facilities per the Town Facility Condition Assessment Study and Capital Master Improvement Plan. | Design, Physical, & Acquisition | TA/Facility Coordinator | Department of Public Works | Select Board | Finance Committee |  | Special Projects | Town funds | [6 empty] | $$$$ = $1m+ | Short-Term (0-3 years) | Facility Condition Assesemnt | Capital Improvement Plan
Core Theme 5 | C | 5.C1 | Evaluate the potential to develop a volunteer program through the Elementary and Masconomet Regional Schools, including the high school's volunteer requirement, local Scouts troops, and others, to aid in occasional, supplemental caretaking for Topsfield’s public spaces. | Capacity Building | School Departments | Department of Public Works | Elementary and Masconomet School Committees |  | Scouts | Sustainability Committee | Town operating budget | [6 empty] | $ = less than $50k | Medium-Term (4-7 years) | High school's volunteer requirement
Core Theme 5 | C | 5.C2 | Create a working list of "Wishlist" projects for departments to add to as necessary for volunteers to assist with. | Programmatic | Town Administrator | Council on Aging | Council on Aging | Elementary and Masconomet School Committees |  |  | Town operating budget | [6 empty] | $$$$ = $1m+ | Short-Term (0-3 years)
Core Theme 5 | D | 5.D1 | The Town should adopt balanced budgets in which current revenues (non-one-time) equal or exceed current expenditures. The Finance Committee’s budget proposal to the Town Meeting will strive to include a financial plan including all general and enterprise funds and activities for the ensuing fiscal year, an accompanying budget message, and supporting documents. | Regulatory & Policy | Town Administrator | Town Accountant | Select Board | Finance Committee | Masconomet Regional Schools |  | Town operating budget | [6 empty] | $ = less than $50k | Short-Term (0-3 years) | Topsfield Financial Policy Guidelines
Core Theme 5 | D | 5.D2 | Each year the Town Administrator, in consultation with the Finance Committee, will work to prepare a five-year Financial Forecast and a five-year Capital Improvement Plan. | Regulatory & Policy | Town Administrator | Town Accountant | Finance Committee | Select Board |  |  | Town operating budget | [6 empty] | $ = less than $50k | Short-Term (0-3 years) | Topsfield Financial Policy Guidelines
Core Theme 5 | D | 5.D3 | The Town will maintain a personnel system that accurately tracks authorized, filled, and unfilled positions as well as their funding source. Pay plans and pay rates will be regularly monitored to ensure accuracy and compliance with labor contracts and personnel policies. | Regulatory & Policy | Town Administrator | Town Accountant | Select Board | Finance Committee |  |  | Town operating budget | [6 empty] | $ = less than $50k | Short-Term (0-3 years) | Topsfield Financial Policy Guidelines
Core Theme 5 | D | 5.D4 | The Town will continue to utilize accounting practices that best conform to generally accepted accounting principles (GAAP) set forth by the Governmental Accounting Standards Board (GASB). | Regulatory & Policy | Town Accountant | Treasurer/Collector | Finance Committee | Select Board |  |  | Town operating budget | [6 empty] | $ = less than $50k | Short-Term (0-3 years) | Topsfield Financial Policy Guidelines
Core Theme 5 | D | 5.D5 | The Town should follow the guidance contained in the Inspector General’s “The Chapter 30B Manual: Procuring Supplies, Services and Real Property” to comply with the requirements of M.G.L. Ch. 30B. | Regulatory & Policy | Town Administrator | Town Accountant | Select Board | Finance Committee |  | Purchasing Agent | Town operating budget | [6 empty] | $ = less than $50k | Short-Term (0-3 years) | Topsfield Financial Policy Guidelines
Core Theme 5 | D | 5.D6 | All efforts to collaborate between the Select Board, Finance Committee, and the local School Committee will be made to ensure transparency and coordination throughout the budgeting process. This may include holding joint meetings as necessary and feasible. | Capacity Building | Town Administrator | Superintendent of School Departmentss | Elementary and Masconomet School Committees | Finance Committee | Masconomet Regional Schools |  | Town operating budget | [6 empty] | $ = less than $50k | Short-Term (0-3 years) | Topsfield Financial Policy Guidelines
Core Theme 5 | E | 5E.1 | Reorient the school curriculum towards real-world readiness and 21st century competencies through a curriculum development and review process, student outcomes, assessments, and reporting systems. | Regulatory & Policy | Superintendent of School Departmentss | School Departments | Elementary and Masconomet School Committees |  | Masconomet Regional Schools |  | Town operating budget | [6 empty] | $ = less than $50k | Medium-Term (4-7 years) | Masconomet Strategic Plan
Core Theme 5 | E | 5E.2 | Meet individual student learning goals and enhance teaching practices through reviewing student service practices and programming, strengthening teacher collaboration systems and professional learning, and establishing ways to highlight successes and areas for improvement. | Programmatic | Superintendent of School Departmentss | School Departments | Elementary and Masconomet School Committees |  | Masconomet Regional Schools |  | Town operating budget | [6 empty] | $$ = $50k-$250k | Medium-Term (4-7 years) | Masconomet Strategic Plan
Core Theme 5 | E | 5E.3 | Foster a safe, trusting, and joyful school culture where students and adults thrive and grow through developing a comprehensive system to support the development of social-emotional competencies and positive mental health. | Regulatory & Policy | Superintendent of School Departmentss | School Departments | Elementary and Masconomet School Committees |  | Masconomet Regional Schools |  | Town operating budget | [6 empty] | $$ = $50k-$250k | Medium-Term (4-7 years) | Masconomet Strategic Plan
Core Theme 5 | E | 5E.4 | Build internal and external relationships through the development of mentoring and advisory programs to support both adults and students in the school. | Programmatic | Superintendent of School Departmentss | School Departments | Elementary and Masconomet School Committees |  | Masconomet Regional Schools |  | Town operating budget | [6 empty] | $$ = $50k-$250k | Medium-Term (4-7 years) | Masconomet Strategic Plan
Core Theme 5 | E | 5E.5 | Implement a capital plan to ensure school facilities support the type of learning envisioned in the schools’ vision and values. | Design, Physical, & Acquisition | Superintendent of School Departmentss | School Departments | Elementary and Masconomet School Committees | Finance Committee | Masconomet Regional Schools |  | Town budget | [6 empty] | $$$ = $250k-$1m | Medium-Term (4-7 years) | Masconomet Strategic Plan | Masconomet Capital Planning Process

## Strategy Tracker
Core Theme | Goal | Strategy Code | Strategy Narrative | Status | Legend |  | Status by Core Theme
Core Theme 1 | A | 1.A1 | Consider amending the Open Space Residential Design bylaw to align with the Open Space Design / Natural Resource Protection Zoning model bylaw. |  |  | Completed Strategy |  | Core Theme 1 | Core Theme 2 | Core Theme 3 | Core Theme 4 | Core Theme 5 | Total
Core Theme 1 | A | 1.A2 | Provide guidelines for and education on installing and maintaining sustainable landscapes on public and private lands, for example, through the Greenscapes North Shore Coalition’s guidelines or other readily available resources. |  |  | In Progress | Completed Strategy | 0 | 0 | 0 | 0 | 0 | 0
Core Theme 1 | A | 1.A3 | Increase involvement with regional collaborations (e.g., Ipswich River Water Association) to help meet common water quality, groundwater protection, and stormwater management goals and objectives. |  |  | Decided not to persue | In Progress | 0 | 0 | 0 | 0 | 0 | 0
Core Theme 1 | A | 1.A4 | Develop a specific policy and process by which the Town determines whether to exercise its right of first refusal under Chapter 61 |  |  | Not yet started | Decided not to persue | 0 | 0 | 0 | 0 | 0 | 0
Core Theme 1 | A | 1.A5 | Use grants and other funding mechanisms to purchase conservation restrictions or acquire prioritized high-value conservation land designated on the Town's priority list, especially properties that abut existing open space and recreational land. The Town could also partner with a regional land trust on acquisition or holding conservation restrictions. |  |  |  | Not yet started | 0 | 0 | 0 | 0 | 0 | 0
Core Theme 1 | B | 1.B1 | Collaborate and support revising and resurrecting the existing Historical Commission’s self-guided historic walking route centered around the Town Center, share it via the website, make paper copies available, and create a virtual town-wide tour. |  |  |  | Total | 0 | 0 | 0 | 0 | 0 | 0
Core Theme 1 | B | 1.B2 | Identify, assess, and prioritize areas for new local historic districts, including the potential for a floating district to protect thematic resources that are not co-located.
Core Theme 1 | B | 1.B3 | Develop incentives for private property owners to invest in and maintain historic structures and educate private property owners of historic structures about existing incentives.
Core Theme 1 | B | 1.B4 | Continue partnerships with the Topsfield Historic Commission, Friends of the Topsfield Library, and Topsfield Historical Society to build public knowledge and tourism base for of historical figures and events (e.g., Salem witch trials, religious history, indigenous history, agricultural history, etc.).
Core Theme 1 | B | 1.B5 | Explore opportunities to install wayfinding signage, especially in the Historic District.
Core Theme 1 | C | 1.C1 | Seek grants to incentivize private water storage and groundwater recharge through a no/low-cost rain barrel program.
Core Theme 1 | C | 1.C2 | Educate the public on sustainability and resiliency topics, such as water conservation in tandem with their water bills, renewable energy options, and solid waste disposal.
Core Theme 1 | C | 1.C3 | Establish a Solid Waste Advisory Committee to explore new services, expand existing services, and educate residents about programs that improve recycling rates, encourage composting, and reduce the costs of waste being landfilled. Examples might be to expand bi-weekly recycling to weekly pickup and set up a “swap shed” where residents can exchange unwanted, still-usable items.
Core Theme 2 | A | 2.A1 | Update the Topsfield Complete Streets Prioritization Plan to identify what has already been accomplished and where to prioritize investment in biking infrastructure around the Town, such as bike parking at municipal facilities and open spaces, public repair stations in strategic locations, and bike lanes along major thoroughfares.
Core Theme 2 | A | 2.A2 | Update the Topsfield Complete Streets Prioritization Plan to identify what has already been accomplished and where to prioritize infrastructure improvements at key intersections, such as Route 1 and Route 97, Route 97 and Main Street, Central Street and Route 1, and Washington Street and Boxford Road.
Core Theme 2 | A | 2.A3 | Update the Topsfield Complete Streets Prioritization Plan to identify what has already been accomplished and where to prioritize pedestrian access across the Town, such as Town facilities, school buildings, open spaces, and major thoroughfares.
Core Theme 2 | A | 2.A4 | Conduct an ADA audit of key corridors in town and the Rail Trail to identify locations needing improvements, such as curb ramps, crosswalks, and accessible pedestrian signals.
Core Theme 2 | B | 2.B1 | Encourage the development of multi-family, non-age restricted housing in the Business Village, Business Highway, Business Highway North, and Business Park Districts through existing and newly proposed zoning and a new MBTA district.
Core Theme 2 | B | 2.B2 | Establish a Housing Advisory Committee. The Housing Advisory Committee could advocate for zoning changes in response to housing needs, improve town capacity to implement housing strategies and policies, build public and political support for Topsfield's housing goals, do community outreach and education, and foster partnerships with regional housing organizations.
Core Theme 2 | B | 2.B3 | Seek funding and a consultant to create a housing plan to analyze housing needs, evaluate the market feasibility and impacts of zoning changes, and work with the Town to identify other regulatory, programmatic, coordination, and capacity strategies.
Core Theme 2 | C | 2.C1 | Explore options to reinstate the Topsfield Park and Ride bus service to offer options to local commuter rail stations and/or commuting into Boston.
Core Theme 2 | C | 2.C2 | Collaborate with the RMV to host regular Older Adult safe driving workshops for residents and caregivers to extend independent living options for older adults and reduce related crashes in Town.
Core Theme 2 | C | 2.C3 | Seek funding opportunities to expand the Council on Aging shuttle bus capacity, service routes, vehicle type, adding lift-assists, and ridership requirements.
Core Theme 2 | C | 2.C4 | Investigate the potential use of Council on Aging vehicle(s) for on-demand shuttle use during off hours.
Core Theme 3 | A | 3.A1 | Regularly review and update zoning downtown and in commercial areas on Route 1 to be conducive to development by allowing more by-right target industries as new commercial uses arise.
Core Theme 3 | A | 3.A2 | Capitalize on residents’ overwhelming support for increased business activity by advancing market-ready economic development opportunities.
Core Theme 3 | A | 3.A3 | Encourage and incentivize the development of a restaurant or pub in the downtown area to enhance the vibrancy and build community through actively seeking out innovative and creative programs as well as formal paths such as federal and state grants.
Core Theme 3 | A | 3.A4 | Continue to invest in beautification and placemaking initiatives downtown to attract residents and visitors, through ongoing stewardship of existing amenities, and new placemaking initiatives as maintenance capacity allows.
Core Theme 3 | A | 3.A5 | Explore opportunities to expand wastewater infrastructure capacity downtown.
Core Theme 3 | A | 3.A6 | Investigate options for design guidelines for Topsfield's commercial districts or modify the site plan review standards to ensure new development is compatible with the Town, as a part of the site plan review process.
Core Theme 3 | B | 3.B1 | Work proactively with existing landowners to support the redevelopment of vacant or underutilized properties on Route 1.
Core Theme 3 | B | 3.B2 | Support existing business retention and expansion through open communication and coordination with business owners.
Core Theme 3 | C | 3.C1 | Explore hiring a Community Development Director or Town Planner to support small businesses, take advantage of economic development opportunities (e.g., financing incentives, grants, etc.), and develop a marketing strategy for attracting new business that aligns with the Town's vision and goals.
Core Theme 3 | C | 3.C2 | Develop and communicate clear and standardized guidelines and procedures for prospective entrepreneurs, including a point-person to speak with at the Town and user-friendly website interfaces (contingent on additional Town capacity).
Core Theme 3 | C | 3.C3 | Expand awareness of volunteer opportunities and strengthen community partnerships related to economic development and entrepreneurship (Topsfield Community Partnership).
Core Theme 3 | C | 3.C4 | Cultivate strong working relationships between the Town and key businesses/ economic development players, either formally (i.e., through a local or regional Business Chamber) or informally through open communication and mutual respect.
Core Theme 3 | C | 3.C5 | Continue to support and promote small businesses and local farms, including events showcasing local businesses.
Core Theme 4 | A | 4.A1 | Explore opportunities to expand the Recreation Department's capacity through a Community Development Director and/or Recreation Director.
Core Theme 4 | A | 4.A2 | Continue supporting and collaborating with local groups to offer historical and cultural education-based events for residents and promote volunteerism in the community, for example through the Topsfield Public Library, the Historical Society, and Council on Aging.
Core Theme 4 | A | 4.A3 | Continue to host community events for residents and visitors near the Town Center and Town Common area, such as the Holiday on the Green and HomeGrown Market.
Core Theme 4 | A | 4.A4 | Explore intergenerational programs to connect youth and young adults with older adults.
Core Theme 4 | A | 4.A5 | Update and maintain a town-wide online shared event coordination calendar.
Core Theme 4 | B | 4.B1 | Expand Topsfield Top 10 Newsletter to proactively market upcoming events and opportunities in Town.
Core Theme 4 | B | 4.B2 | Continue to advance the use of electronic applications for permit submittal and review.
Core Theme 4 | B | 4.B3 | Continue modernizing policies and implement staff training on social media as an effective communication tool.
Core Theme 4 | B | 4.B4 | Support the Town library in its goals to enable all residents access to current technologies and to provide education on how to work those technologies.
Core Theme 4 | B | 4.B5 | Support the schools in their goal to invest in modern teaching and learning technologies.
Core Theme 4 | C | 4.C1 | Implement the Topsfield Open Space and Recreation Plan (OSRP 2019) through its seven-year Action Plan.
Core Theme 4 | C | 4.C2 | Increase Town beautification efforts by identifying places for permanent and temporary public art and landscaping installations.
Core Theme 4 | C | 4.C3 | Expand public-private partnerships to activate public and private facilities in off-hours for cultural activities and to boost indoor athletic and art-based recreation opportunities. Ideas may include the school buildings, Public Hall, library, Tri-Town Council Gym, Emerson Center, and Topsfield Fairgrounds.
Core Theme 4 | C | 4.C4 | Support ongoing efforts to create a linked trail network per the 2019 Open Space and Recreation Plan.
Core Theme 4 | C | 4.C5 | Consider opportunities to promote Recreational Amenities such as the new Pump Track and Pye Brook Disc Golf Course to host races and tournaments to draw tourism.
Core Theme 4 | C | 4.C6 | Create an updated ADA Transition Plan to improve access to public facilities, playgrounds, and open spaces for people with disabilities.
Core Theme 5 | A | 5.A1 | Seek grant opportunities to use green building design components in any municipal or school renovations or improvements, such as weatherization, material sourcing, indoor environmental quality, water usage, and waste disposal.
Core Theme 5 | A | 5.A2 | Implement the recommendations in the Hazard Mitigation Plan/ Municipal Vulnerability Preparedness Plan (2021).
Core Theme 5 | A | 5.A3 | Continue to invest in energy-efficient equipment and facilities for municipal operations, including schools, that reduce carbon emissions, energy consumption, and costs.
Core Theme 5 | A | 5.A4 | Prioritize electric or energy-efficient municipal vehicles whenever possible as new vehicles are purchased.
Core Theme 5 | A | 5.A5 | Build on recent efforts, such as solar-powered streetlamps, to increase solar and other alternative energy sources at Town facilities and in Topsfield's public spaces.
Core Theme 5 | A | 5.A6 | Develop a greenhouse gas inventory to help understand Topsfield's baseline of significant sources of emissions, establish a greenhouse gas emission reduction goal, and document current measures taken to reduce greenhouse gas emissions. Additionally, develop an Action Plan to address gaps focusing on municipal energy reduction with high return on investment.
Core Theme 5 | B | 5.B1 | Continue supporting all departments to compete for grants that could provide training, planning support, or funds for physical improvements to roads and facilities.
Core Theme 5 | B | 5.B2 | Continue to maintain and upgrade the municipal water supply infrastructure and capacity (e.g., through shared or alternative water resources such as regional planning with the Ipswich Watershed, the Salem-Beverly Water Supply Board, or MWRA).
Core Theme 5 | B | 5.B3 | Identify where different departments or cross-departmental issues may require more intensive study (e.g., public safety building feasibility study) and identify funding needed to perform those studies.
Core Theme 5 | B | 5.B4 | Explore opportunities to enhance municipal services utilizing programs and funding opportunities from the Massachusetts Rural Policy Plan.
Core Theme 5 | B | 5.B5 | Support capital improvements to municipal facilities per the Town Facility Condition Assessment and Capital Improvement Plan.
Core Theme 5 | C | 5.C1 | Evaluate the potential to develop a volunteer program through the Masconomet Regional Schools, including the high school's volunteer requirement, local Scouts troops, and others, to aid in caretaking for Topsfield’s public spaces.
Core Theme 5 | C | 5.C2 | Create a working list of "Wishlist" projects for departments to add to as necessary for volunteers to assist with.
Core Theme 5 | D | 5.D1 | The Town should adopt balanced budgets in which current revenues (non-one-time) equal or exceed current expenditures. The Finance Committee’s budget proposal to the Town Meeting will strive to include a financial plan including all general and enterprise funds and activities for the ensuing fiscal year, an accompanying budget message, and supporting documents.
Core Theme 5 | D | 5.D2 | Each year the Town Administrator, in consultation with the Finance Committee, will work to prepare a five-year Financial Forecast and a five-year Capital Improvement Plan.
Core Theme 5 | D | 5.D3 | The Town will maintain a personnel system that accurately tracks authorized, filled, and unfilled positions as well as their funding source. Pay plans and pay rates will be regularly monitored to ensure accuracy and compliance with labor contracts and personnel policies.
Core Theme 5 | D | 5.D4 | The Town will utilize accounting practices that best conform to generally accepted accounting principles (GAAP) set forth by the Governmental Accounting Standards Board (GASB).
Core Theme 5 | D | 5.D5 | The Town should follow the guidance contained in the Inspector General’s “The Chapter 30B Manual: Procuring Supplies, Services and Real Property” to comply with the requirements of M.G.L. Ch. 30B.
Core Theme 5 | D | 5.D6 | All efforts to collaborate between the Select Board, Finance Committee, and the local School Committee will be made to ensure transparency and coordination throughout the budgeting process. This may include holding joint meetings as necessary and feasible.
Core Theme 5 | E | 5E.1 | Reorient the school curriculum towards real-world readiness and 21st century competencies through a curriculum development and review process, student outcomes, assessments, and reporting systems.
Core Theme 5 | E | 5E.2 | Meet individual student learning goals and enhance teaching practices through reviewing student service practices and programming, strengthening teacher collaboration systems and professional learning, and establishing ways to highlight successes and areas for improvement.
Core Theme 5 | E | 5E.3 | Foster a safe, trusting, and joyful school culture where students and adults thrive and grow through developing a comprehensive system to support the development of social-emotional competencies and positive mental health.
Core Theme 5 | E | 5E.4 | Build internal and external relationships through the development of mentoring and advisory programs to support both adults and students in the school.
Core Theme 5 | E | 5E.5 | Implement a capital plan to ensure school facilities support the type of learning envisioned in the schools’ vision and values.

## Metrics Rubric
Core Theme | Metric | Data Source | Starting # (MM/DD/YYYY) | Target | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  |  | 2030 |  |  |  | 2031 |  |  |  | 2032 |  |  |  | 2033 |  |  |  | 2034
[5 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Core Theme 1 | Number of residents who use the Town's yard waste collection program |  |  | #,###
Core Theme 1 | Total pounds of solid waste, recycling, compost, and hazardous material produced in Topsfield |  |  | #,### lbs
Core Theme 1 | Compliance with NPSED permit requirements for MS4 |  |  | Y/N
Core Theme 1 | Number of gallons of drinking water available per day (average) |  |  | #,### gal
Core Theme 1 | Number of gallons of water used by town per day (average) |  |  | #,### gal
Core Theme 1 | Water used/water available ratio (average) |  |  | ##%
Core Theme 1 | Number of historic resources in Topsfield that are protected through a preservation restriction, acquisition, or local historic district designation | MHP MACRIS |  | #,###
Core Theme 1 | Townwide energy usage |  |  | ## Btu or ### kwh
Core Theme 2 | Number of non-single family housing units (planned + in progress + completed) since start date | Town Permitting Data |  | ##
Core Theme 2 | Number of affordable housing planning efforts (planned + in progress + completed) since start date | Request updated SHI from EOHLC |  | ##
Core Theme 2 | H + T index score (housing and transportation costs as a percentage of household income) | H + T Affordability Index |  | ##%
Core Theme 2 | Number of Complete Streets projects (planned + in progress + completed) since start date |  |  | ##
Core Theme 3 | Number of commercial development projects (planned + in progress + completed) since start date | Town Permitting Data |  | ##
Core Theme 3 | Square footage of vacant industrial and commercial space |  |  | ## sq ft
Core Theme 3 | Number of mixed-use buildings developed (planned + in progress + completed) since start date | Town Permitting Data |  | ##
Core Theme 3 | Tax revenue from industrial and commercial uses | Town Assessor / Board of Assessors |  | $#,###
Core Theme 4 | Number of public facilities, open spaces, and playgrounds that meet and exceed ADA compliance | ADA Coordinator |  | ##
Core Theme 4 | Number of town permitting processes moved to virtual/hybrid alternatives |  |  | ##
Core Theme 4 | Digital engagement analytics: Social Media Engagement | Variety of platforms will collect this information for you |  | #,###
Core Theme 4 | Digital engagement analytics: Newsletter Recipients | Digital Communications |  | #,###
Core Theme 4 | Digital engagement analytics: Digital Engagement Platforms (if acquired) | Digital Communications |  | #,###
Core Theme 4 | Number of open space and recreational amenity improvements (planned + in progress + completed) since start date |  |  | ##
Core Theme 5 | Number of grants Topsfield has received for road and facility improvements, since start date |  |  | ##
Core Theme 5 | Number of capital improvement projects for improving municipal facilities (planned + in progress + completed) since starting date |  |  | ##
Core Theme 5 | Municipal employee retention rate (annual) | Town Administrator/ HR |  | ##%
Core Theme 5 | Total amount of renewable energy used by municipal properties |  |  | ## Btu or ### kwh
Core Theme 5 | Total amount of fossil fuel energy used by municipal properties |  |  | ## Btu or ### kwh
Core Theme 5 | Total amount of energy (renewable + fossil fuel) used by municipal properties |  |  | ## Btu or ### kwh